SALESFORCE IMPLEMENTATION GUIDE

Resources & Skills for a New Salesforce Org

Sales Cloud, Service Cloud and Revenue Cloud / Revenue Management

A practical planning guide for assembling the implementation team, platform resources, environments, skills and governance needed to deliver an integrated customer and product-to-cash platform.

Important product decision Salesforce documentation increasingly refers to the newer Revenue Cloud platform as Revenue Management. Confirm whether the program will use the newer platform or legacy Salesforce CPQ and Billing before estimating, staffing or designing migration paths.

# 1. Executive summary

This program should be treated as a cross-functional transformation, not simply a CRM configuration. Sales, service and product-to-cash processes share customer, product, price, contract, order and asset data. Decisions made in one workstream can therefore create downstream constraints in the others.

For a moderately complex implementation, plan for a core delivery team of approximately 10-18 people plus business subject-matter experts. A small, low-integration deployment may operate with 6-8; a global or highly regulated product-to-cash program may require materially more.

# 2. Core implementation team

The following roles form the minimum multidisciplinary capability. Several roles can be combined in a small program, but accountability should remain explicit.

| Resource | Primary responsibility | Typical need |
| --- | --- | --- |
| Executive sponsor | Funding, priorities and cross-functional decisions | Part-time |
| Business product owner | Scope, backlog, value and acceptance | 50-100% |
| Program / project manager | Plan, dependencies, risk, budget and governance | Full-time |
| Salesforce solution architect | End-to-end data, security, integration and platform design | Full-time initially |
| Business analyst / process designer | Requirements, process maps and user stories | 1-3 |
| Salesforce administrator | Configuration, permissions, Flow, reports and supportability | 1-2 |
| Salesforce developer | Apex, Lightning and complex extensions | 1-3 |
| Integration architect / developer | ERP, identity, telephony, tax, payments and middleware | 1-3 |
| Data architect / migration specialist | Data model, cleansing, migration and reconciliation | 1-2 |
| QA / test lead | Regression, integration, performance and UAT | 1-3 |
| DevOps / release engineer | Git, CI/CD, environments and deployments | 0.5-1 |
| Change and adoption lead | Training, communications and adoption measurement | 1 |
| Security / privacy specialist | Identity, access, audit, retention and compliance | Part-time |

# 3. Business workstreams and subject-matter experts

## Sales Cloud

Lead generation, qualification and conversion

Account, contact and customer hierarchy management

Opportunity stages, sales methodology and pipeline governance

Forecasting, quotas, territories and sales performance measures

Partner or channel sales, where applicable

Approval and discount authority

Sales reporting, dashboards and adoption metrics

## Service Cloud

Case intake, classification, routing, queues and escalation

Service levels, entitlements and milestones

Knowledge creation, approval, publication and retirement

Omni-Channel, email, chat, messaging and voice

Contact-center operations and quality management

Complaints, returns, warranties and field service, if applicable

Customer portals, self-service and service analytics

## Revenue Cloud / Revenue Management

This is normally the most specialized workstream. It needs SMEs who understand the complete product-to-cash lifecycle, including finance and operational controls.

Product ownership, catalog structure, bundles, attributes and selling models

Pricing methods, price books, discount policies and approval thresholds

Quote configuration and generation

Contracting, legal clauses and commercial governance

Order capture, orchestration and fulfillment handoffs

Subscriptions, amendments, renewals, cancellations and asset lifecycle

Usage or consumption rating, if applicable

Billing schedules, invoicing, credits, taxation, payments and collections

ERP, finance, tax and revenue-recognition integration boundaries

Staffing principle A Salesforce configurator without product-to-cash domain expertise is not sufficient for Revenue Cloud. Pair platform specialists with RevOps, product, finance, tax, legal and order-management owners.

# 4. Required technical skills

Salesforce data modeling and the shared Sales, Service and Revenue object model

Sales Cloud configuration, forecasting, territories and pipeline design

Service Cloud, Knowledge, Omni-Channel, entitlements and contact-center patterns

Revenue Cloud catalog, configuration, pricing, quoting, contracts, orders, assets and billing

Flow, approval automation and error-handling patterns

Apex and Lightning Web Components for justified extensions

REST, SOAP, Bulk API, Platform Events and event-driven integration

Identity, SSO, MFA, connected apps, named credentials and integration-user design

Role hierarchy, sharing, permission sets, field-level security and auditability

Data migration, cleansing, deduplication, reconciliation and archival

Reports, dashboards, analytics and KPI design

Salesforce CLI, Git, CI/CD, test automation and release governance

Platform limits, performance, large data volumes and resilient solution design

Training, adoption, operating model and post-go-live support

## Relevant credentials

Certifications are useful evidence of foundational knowledge, but they do not replace implementation experience. Relevant credentials include:

Salesforce Administrator and Platform App Builder

Sales Cloud Consultant and Service Cloud Consultant

Revenue Cloud Consultant

Platform Developer I

Data Architect, Sharing and Visibility Architect, and Integration Architect

Application Architect or System Architect for senior design leadership

# 5. Platform, environment and delivery resources

Establish the delivery lifecycle before feature build begins. Production should never be the primary development, integration-test or training environment.

Production org

Individual Developer sandboxes and/or scratch orgs

Shared integration environment

QA and system-test environment

User acceptance testing environment

Training environment

Partial Copy or Full Copy sandbox for realistic end-to-end testing

Git repository as the metadata source of truth

Salesforce CLI and automated CI/CD pipeline

Automated test framework and regression suite

Test-data generation, masking and refresh procedures

Architecture, requirements, decision and operating-model repository

Release calendar, change control and incident-management process

Environment sizing Sandbox types and quantities depend on the Salesforce edition and purchased entitlements. Include refresh cadence, data masking, release-preview strategy and integration endpoint management in the environment plan.

# 6. Licensing and connected-system checklist

## Licensing decisions

Salesforce edition and geographic / Hyperforce requirements

Sales Cloud, Service Cloud and Revenue Cloud user counts and personas

Revenue Cloud Advanced and/or Billing functional entitlements

Digital Engagement, Voice, telephony or contact-center capabilities

Experience Cloud external-user licensing

Knowledge, Field Service and analytics requirements

Shield encryption, event monitoring, audit and compliance requirements

Sandbox types, storage, API capacity and integration-user licences

## Likely integrations

ERP, general ledger and accounts receivable

Master data management and product lifecycle management

Identity provider and user provisioning

Marketing automation and customer data platforms

Contact-center and telephony platforms

E-commerce and partner channels

Tax engines, payment gateways and electronic signature

Contract lifecycle management

Data warehouse, lakehouse and enterprise reporting

# 7. Essential design deliverables

Business capability map and agreed scope boundaries

Current-state and target-state process maps

Phased roadmap, dependencies and measurable outcomes

System context, integration and data-flow diagrams

Canonical customer, product, pricing, contract, order and asset models

Product catalog ownership and governance model

Pricing, discount and approval decision tables

Quote-to-order-to-invoice process and exception design

Security personas, access matrix and data-classification model

Data retention, archival, migration and reconciliation plans

Environment, source-control and deployment strategy

Test strategy, requirements traceability and acceptance criteria

Reporting and KPI catalogue

Support model, release governance and adoption plan

# 8. Recommended implementation sequence

Establish program governance, architecture principles, identity, security, DevOps and the shared customer/product data model.

Implement foundational Sales Cloud processes and reporting.

Implement Service Cloud and customer-service integrations.

Build the Revenue Cloud catalog, pricing, quoting and commercial approvals.

Add contracts, orders, assets, amendments, cancellations and renewals.

Add billing, tax, usage and ERP/finance integrations where in scope.

Complete end-to-end product-to-cash testing, data migration, training and phased rollout.

Architecture recommendation Design Revenue Cloud from the beginning even if it goes live later. Product, price book, account, contract, order and asset decisions made during the Sales Cloud phase can otherwise create expensive rework.

# 9. Readiness gate before build

Configuration should begin only after the program can answer the following questions with named owners and documented decisions:

Which Revenue Cloud product generation and licence set is being implemented?

What is the authoritative source for customer, product, price, contract, order and billing data?

Which processes will remain in ERP, finance, tax, CLM, telephony or other platforms?

Which user and integration personas require access to which data and operations?

What are the migration volumes, quality issues, retention rules and reconciliation tolerances?

Which end-to-end scenarios constitute go-live acceptance?

Who owns the product catalog, pricing rules, service taxonomy and release process after go-live?

# 10. Salesforce reference resources

Prepare for a Revenue Management implementation

Revenue Cloud / Revenue Management product documentation

Salesforce Certified Revenue Cloud Consultant

Salesforce sandbox types and management practices

When to use a Salesforce sandbox

Salesforce Well-Architected framework

Salesforce Well-Architected security guidance

Salesforce Well-Architected resilience guidance

Licensing, naming and product capabilities change over time. Validate the final SKU, edition, regional, limit and coexistence assumptions with Salesforce and the implementation partner before contract signature and solution baseline approval.